## Web Dev Project Budget
Web Development Project Budget
| Client's Name: | The total fictional Recipe company |  |  |  | Location | Belgium
| Project Code: | ABFE1234567890 |  |  |  | Start Date | 30/04/2022
[6 empty] | End Date | 20/06/2022
Sr. No. | Particulars / Details |  |  | Est. Hrs. | Rate /Hr. | Amount
1 | Wireframe Adobe XD |  |  | 2 | 43.75 | 87.5
2 | Database setup / model |  |  | 2 | 43.75 | 87.5
3 | Firebase setup |  |  | 1 | 43.75 | 43.75
4 | Authentication setup / testing |  |  | 24 | 43.75 | 1050
5 | Routing |  |  | 4 | 43.75 | 175
6 | HTML Layout and CSS |  |  | 60 | 43.75 | 2625
7 | Recipe form / add & edit |  |  | 24 | 43.75 | 1050
8 | Detail page per recipe |  |  | 8 | 43.75 | 350
9 | Shopping list |  |  | 2 | 43.75 | 87.5
10 | Title bar and header |  |  | 8 | 43.75 | 350
11 | Designing and finalisinng remaining pages and sub pages. | Total Pages | Est. Hrs./Pg. | 24 | 43.75 | 1050
|  | 3 | 8
12 | Client's Training |  |  | 2 | 43.75 | 87.5
13 | Basic SEO for Site |  |  | 2 | 43.75 | 87.5
Semi-Total |  |  |  | 163 |  | 7131.25
Contingency |  | + | 10% | 16.3 | 43.75 | 713.125
Total |  |  |  | 179.3 |  | 7844.375
Project Estimates | [5 empty] | 7844.375