## Web Dev Project Budget
Web Development Project Budget
| Client's Name: | ABC Company |  |  |  | Location | Belgium
| Project Code: | ABFE1234567890 |  |  |  | Start Date | 2019-11-01
[6 empty] | End Date | 2019-12-01
Sr. No. | Particulars / Details |  |  | Est. Hrs. | Rate /Hr. | Amount
1 | Designing Page Layout, Colour Scheme, Buttons etc. |  |  | 15 | 350 | 5250
2 | Home page content finalization with corrections |  |  | 8 | 350 | 2800
3 | About Us Page and Services Page Layout |  |  | 12 | 350 | 4200
4 | About Us Page and Services Page Layout Content |  |  | 3 | 350 | 1050
5 | About Us Page and Services Page Finalization |  |  | 15 | 350 | 5250
6 | CSS Coding for layout |  |  | 12 | 350 | 4200
7 | CSS Coding for Payment Gateway |  |  | 15 | 350 | 5250
8 | Blog Page design Layout |  |  | 5 | 350 | 1750
9 | Domain Registration |  |  | 1 | 350 | 350
10 | Hosting |  |  | 1 | 350 | 350
11 | CSS Coding for Payment Gateway |  |  | 1 | 350 | 350
12 | Logo Creating/Designing. |  |  | 1 | 350 | 350
13 | Blog Page design Layout Finalization |  |  | 2 | 350 | 700
14 | Proof Reading of the Main Pages |  |  | 20 | 350 | 7000
15 | Additional Editing as per client's requirement |  |  | 5 | 350 | 1750
16 | Designing and finalisinng remaining pages and sub pages. | Total Pages | Est. Hrs./Pg. | 100 | 350 | 35000
|  | 20 | 5
17 | Creating contact forms |  |  | 10 | 350 | 3500
18 | Finalizing Contact Form |  |  | 2 | 350 | 700
19 | Payment Gateway installation |  |  | 5 | 350 | 1750
20 | Testing, trouble shooting and finalising |  |  | 6 | 350 | 2100
21 | Developing Dynamic Application. |  |  | 1 | 350 | 350
22 | Testing, trouble shooting and finalising data driven report generations. |  |  | 10 | 350 | 3500
23 | Initial support to client's |  |  | 5 | 350 | 1750
24 | Client;'s Training |  |  | 15 | 350 | 5250
25 | Basic SEO for Site |  |  | 1 | 350 | 350
26
27
28
Semi-Total |  |  |  | 271 |  | 94850
Contingency |  | + | 10% | 27.1 | 350 | 9485
Total |  |  |  | 298.1 |  | 104335
Project Estimates | [5 empty] | 104335